Mt. Washington Steering Committee Meeting | 7.29.2026 | 6:30-7:30pm

Mt. Washington Branch Library

2049 Beechmont Ave, Cincinnati, OH 45230

- Welcome | 6:35-6:40

- Theme Working Groups Update | 6:40-7:00

  - Goal & Strategy Development – Do groups have updated goals & strategies? Use these to inform finalized theme names.

    - Housing - end of next week for members to update comments

    - Economic development/placemaking - leaders working on draft list - planning to meet again in 2-3 weeks, also meeting with business owners for input

    - Connectivity and Mobility - second meeting included DOT - plan to send out update to group next week

    - Parks and greenspace chair absent, last meeting reviewed 2007 plan

    - Quality of life/Health &Wellness - next meeting 8/4 to review goals and strategies

  - Mapping Implementation – Next working group meetings should focus on where goals and strategies should be implemented (Westwood example)

    - Need to finalize names for multi named groups for final plan

    - Locations for goals to be implemented (see westwood plan starting on page 73 for good examples)

    - Identify lots available for multifamily as is (Sophia has access to a list from the City)

    - Urban design overlay needs updated pictures and building list finalized

  - Meetings to Schedule

    - Housing – Connect with Department of Opportunity and Resident Services (DOORS) and Buildings & Inspections (B&I)

    - Economic Development/Placemaking – Connect with Office of Strategic Growth (OSG); Integrate Urban Design Overlay District into this section of the Plan

    - Connectivity/Mobility – Connect with other communities that have had successful traffic calming on major roads; Meet with Anderson Township about any coordination improvements to be made

    - Parks & Greenspace – Arrange meeting(s) with Miami Tribe of Oklahoma representative, Cincinnati Parks, Tyler Swinney regarding the historic and cultural assets in Stanbery; Connect with Office of Environment and Sustainability on Green Cincinnati Plan integration

    - Quality of Life/Health & Wellness – Connect with Cincinnati Aging & Accessibility; Coordinate meeting between MWCDC, MWCC, and MWCURC with Walnut Hills groups as an example of coordination; Connect with Office of Environment and Sustainability on Green Cincinnati Plan integration

    - All subgroups chairs to meet to review crossover items

- Plan Timeline Discussion | 7:00-7:20

  - Public Meeting #2

    - Materials

      - “What we heard” from kickoff meeting, surveys, etc.

      - Goals & strategies drafts – prioritize & identify partners

      - Geographic focus areas

      - Future land use activity

    - Still on track for 9/12? Time between PM #2 and open house?

      - Thinking we need to go out a little further, but before the end of October. Will send out a poll for availability. (not during blink, or Pumpkin Chuck)

  - After Public Meeting #2

    - Finalize prioritization and timeline

    - Open house with Plan draft

    - Review and approval by City departments & Community Council 🡪 City Planning Commission 🡪 City Council

- Other items/discussion | 7:20-7:30

  - Concluded at 7:12 PM